## Full Product Backlog
Sprint | Epic | Story | Task | Subtask | Issue Type | Status | Priority | Story Point | Description
Sprint 1 | EPIC 2: Product & Inventory Management |  |  |  | Epic | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories |  |  | Story | TODO | High | 5 | Là quản trị viên, tôi muốn quản lý danh mục sản phẩm để dễ dàng phân loại và tổ chức các sản phẩm trong hệ thống.
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.1 Category Management UI |  | Task | TODO | Medium | 2
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.1 Category Management UI | Design Category List Page | Subtask | TODO | Medium
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.1 Category Management UI | Design Add Category Form | Subtask | TODO | Medium
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.1 Category Management UI | Design Edit Category Form | Subtask | TODO | Medium
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.1 Category Management UI | Responsive Category Page | Subtask | TODO | Medium
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.2 Category CRUD API |  | Task | TODO | High | 2
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.2 Category CRUD API | Create Category API | Subtask | TODO | High
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.2 Category CRUD API | Update Category API | Subtask | TODO | High
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.2 Category CRUD API | Delete Category API | Subtask | TODO | High
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.2 Category CRUD API | Get Category List API | Subtask | TODO | Medium
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.3 Category Testing |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.3 Category Testing | Create Category Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.3 Category Testing | Update Category Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 1: Manage Categories | Task 1.3 Category Testing | Delete Category Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products |  |  | Story | TODO | Critical | 8
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.1 Product Management UI |  | Task | TODO |  | 2
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.1 Product Management UI | Design Product List | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.1 Product Management UI | Design Product Detail | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.1 Product Management UI | Design Add Product Form | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.1 Product Management UI | Design Edit Product Form | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.2 Product CRUD API |  | Task | TODO |  | 3
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.2 Product CRUD API | Create Product | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.2 Product CRUD API | Update Product | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.2 Product CRUD API | Delete Product | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.2 Product CRUD API | Get Product Detail | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.2 Product CRUD API | Get Product List | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.3 Product Image Management |  | Task | TODO |  | 2
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.3 Product Image Management | Upload Product Image | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.3 Product Image Management | Delete Product Image | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.3 Product Image Management | Preview Product Image | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.3 Product Image Management | Compress Image | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.4 Product Testing |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.4 Product Testing | CRUD Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.4 Product Testing | Image Upload Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 2: Manage Products | Task 2.4 Product Testing | Validation Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants |  |  | Story | TODO |  | 8
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.1 Variant CRUD |  | Task | TODO |  | 3
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.1 Variant CRUD | Create Variant | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.1 Variant CRUD | Edit Variant | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.1 Variant CRUD | Delete Variant | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.1 Variant CRUD | View Variant | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.2 Variant Pricing |  | Task | TODO |  | 2
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.2 Variant Pricing | Set Variant Price | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.2 Variant Pricing | Update Variant Price | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.2 Variant Pricing | Discount Variant | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.3 Variant Attributes |  | Task | TODO |  | 2
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.3 Variant Attributes | Manage Size | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.3 Variant Attributes | Manage Flavor | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.3 Variant Attributes | Manage Topping | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.3 Variant Attributes | Manage Availability | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.4 Variant Testing |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.4 Variant Testing | CRUD Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.4 Variant Testing | Price Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 3: Manage Product Variants | Task 3.4 Variant Testing | Variant Validation | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 4: Product Detail |  |  | Story | TODO |  | 5
Sprint 1 | EPIC 2: Product & Inventory Management | Story 4: Product Detail | Task 4.1 Product Detail UI |  | Task | TODO |  | 2
Sprint 1 | EPIC 2: Product & Inventory Management | Story 4: Product Detail | Task 4.1 Product Detail UI | Display Product Images | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 4: Product Detail | Task 4.1 Product Detail UI | Display Product Description | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 4: Product Detail | Task 4.1 Product Detail UI | Display Product Variants | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 4: Product Detail | Task 4.2 Product Detail API |  | Task | TODO |  | 2
Sprint 1 | EPIC 2: Product & Inventory Management | Story 4: Product Detail | Task 4.2 Product Detail API | Get Product Detail | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 4: Product Detail | Task 4.2 Product Detail API | Get Product Images | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 4: Product Detail | Task 4.2 Product Detail API | Get Product Variants | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 4: Product Detail | Task 4.3 Detail Testing |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 4: Product Detail | Task 4.3 Detail Testing | UI Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 4: Product Detail | Task 4.3 Detail Testing | API Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 5: Search Products |  |  | Story | TODO |  | 3
Sprint 1 | EPIC 2: Product & Inventory Management | Story 5: Search Products | Task 5.1 Search UI |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 5: Search Products | Task 5.1 Search UI | Search Bar | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 5: Search Products | Task 5.1 Search UI | Search Suggestion | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 5: Search Products | Task 5.2 Search API |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 5: Search Products | Task 5.2 Search API | Search By Name | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 5: Search Products | Task 5.2 Search API | Search By Category | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 5: Search Products | Task 5.3 Search Testing |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 5: Search Products | Task 5.3 Search Testing | Search Result Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 5: Search Products | Task 5.3 Search Testing | Empty Search Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 6: Filter Products |  |  | Story | TODO |  | 3
Sprint 1 | EPIC 2: Product & Inventory Management | Story 6: Filter Products | Task 6.1 Filter UI |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 6: Filter Products | Task 6.1 Filter UI | Category Filter | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 6: Filter Products | Task 6.1 Filter UI | Price Filter | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 6: Filter Products | Task 6.1 Filter UI | Availability Filter | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 6: Filter Products | Task 6.2 Filter API |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 6: Filter Products | Task 6.2 Filter API | Filter By Category | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 6: Filter Products | Task 6.2 Filter API | Filter By Price | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 6: Filter Products | Task 6.2 Filter API | Filter By Stock | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 6: Filter Products | Task 6.3 Filter Testing |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 6: Filter Products | Task 6.3 Filter Testing | Filter Accuracy Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 6: Filter Products | Task 6.3 Filter Testing | Combined Filter Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images |  |  | Story | TODO |  | 3
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images | Task 7.1 Image Upload |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images | Task 7.1 Image Upload | Upload Multiple Images | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images | Task 7.1 Image Upload | Preview Images | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images | Task 7.1 Image Upload | Remove Images | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images | Task 7.2 Image Storage |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images | Task 7.2 Image Storage | Save Image URL | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images | Task 7.2 Image Storage | Optimize Image Size | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images | Task 7.2 Image Storage | Delete Image | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images | Task 7.3 Image Testing |  | Task | TODO |  | 1
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images | Task 7.3 Image Testing | Upload Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images | Task 7.3 Image Testing | Delete Test | Subtask | TODO
Sprint 1 | EPIC 2: Product & Inventory Management | Story 7: Manage Product Images | Task 7.3 Image Testing | File Format Validation | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience |  |  |  | Epic | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart |  |  | Story | TODO | High | 8 | Là khách hàng, tôi muốn thêm sản phẩm vào giỏ hàng để có thể mua nhiều sản phẩm trong một đơn hàng.
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.1 Shopping Cart UI |  | Task | TODO | Medium | 3
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.1 Shopping Cart UI | Design Shopping Cart Page | Subtask | TODO | Medium
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.1 Shopping Cart UI | Display Cart Items | Subtask | TODO | Medium
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.1 Shopping Cart UI | Display Product Variant | Subtask | TODO | Medium
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.1 Shopping Cart UI | Display Total Price | Subtask | TODO | Medium
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.1 Shopping Cart UI | Responsive Shopping Cart | Subtask | TODO | Medium
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.2 Shopping Cart API |  | Task | TODO | High | 3
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.2 Shopping Cart API | Add Product to Cart | Subtask | TODO | High
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.2 Shopping Cart API | Get Cart Items | Subtask | TODO | High
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.2 Shopping Cart API | Update Cart Item | Subtask | TODO | High
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.2 Shopping Cart API | Remove Cart Item | Subtask | TODO | High
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.2 Shopping Cart API | Calculate Total Price | Subtask | TODO | Medium
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.3 Shopping Cart Testing |  | Task | TODO |  | 2
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.3 Shopping Cart Testing | Add Item Test | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.3 Shopping Cart Testing | Remove Item Test | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.3 Shopping Cart Testing | Quantity Update Test | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 1: Shopping Cart | Task 1.3 Shopping Cart Testing | Total Price Test | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 2: Update Cart |  |  | Story | TODO |  | 5
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 2: Update Cart | Task 2.1 Update Quantity |  | Task | TODO |  | 2
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 2: Update Cart | Task 2.1 Update Quantity | Increase Quantity | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 2: Update Cart | Task 2.1 Update Quantity | Decrease Quantity | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 2: Update Cart | Task 2.1 Update Quantity | Validate Stock Quantity | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 2: Update Cart | Task 2.2 Remove Product |  | Task | TODO |  | 2
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 2: Update Cart | Task 2.2 Remove Product | Remove Single Item | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 2: Update Cart | Task 2.2 Remove Product | Clear Shopping Cart | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 2: Update Cart | Task 2.2 Remove Product | Update Cart Summary | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 2: Update Cart | Task 2.3 Cart Testing |  | Task | TODO |  | 1
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 2: Update Cart | Task 2.3 Cart Testing | Quantity Validation | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 2: Update Cart | Task 2.3 Cart Testing | Remove Item Test | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout |  |  | Story | TODO |  | 8
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.1 Checkout UI |  | Task | TODO |  | 3
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.1 Checkout UI | Shipping Information Form | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.1 Checkout UI | Pickup Branch Selection | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.1 Checkout UI | Order Summary | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.1 Checkout UI | Payment Method Selection | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.2 Checkout API |  | Task | TODO |  | 3
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.2 Checkout API | Create Order | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.2 Checkout API | Validate Product Stock | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.2 Checkout API | Save Shipping Address | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.2 Checkout API | Generate Order Number | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.3 Checkout Testing |  | Task | TODO |  | 2
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.3 Checkout Testing | Successful Checkout | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.3 Checkout Testing | Empty Cart Validation | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 3: Checkout | Task 3.3 Checkout Testing | Out of Stock Validation | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment |  |  | Story | TODO |  | 8
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.1 Payment Integration |  | Task | TODO |  | 3
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.1 Payment Integration | COD Payment | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.1 Payment Integration | Online Payment | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.1 Payment Integration | Payment Callback | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.1 Payment Integration | Payment Status Update | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.2 Payment UI |  | Task | TODO |  | 3
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.2 Payment UI | Payment Success Page | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.2 Payment UI | Payment Failed Page | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.2 Payment UI | Payment Loading | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.3 Payment Testing |  | Task | TODO |  | 2
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.3 Payment Testing | Successful Payment | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.3 Payment Testing | Failed Payment | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 4: Payment | Task 4.3 Payment Testing | Cancel Payment | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 5: Order Tracking |  |  | Story | TODO |  | 5
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 5: Order Tracking | Task 5.1 Order Tracking UI |  | Task | TODO |  | 2
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 5: Order Tracking | Task 5.1 Order Tracking UI | Display Order Timeline | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 5: Order Tracking | Task 5.1 Order Tracking UI | Display Order Status | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 5: Order Tracking | Task 5.1 Order Tracking UI | Display Delivery Information | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 5: Order Tracking | Task 5.2 Order Tracking API |  | Task | TODO |  | 2
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 5: Order Tracking | Task 5.2 Order Tracking API | Get Order Status | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 5: Order Tracking | Task 5.2 Order Tracking API | Get Delivery Information | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 5: Order Tracking | Task 5.2 Order Tracking API | Refresh Order Status | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 5: Order Tracking | Task 5.3 Tracking Testing |  | Task | TODO |  | 1
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 5: Order Tracking | Task 5.3 Tracking Testing | Status Update Test | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 5: Order Tracking | Task 5.3 Tracking Testing | Timeline Display Test | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 6: Order History |  |  | Story | TODO |  | 3
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 6: Order History | Task 6.1 Order History UI |  | Task | TODO |  | 1
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 6: Order History | Task 6.1 Order History UI | Display Order List | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 6: Order History | Task 6.1 Order History UI | Filter Orders | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 6: Order History | Task 6.2 Order History API |  | Task | TODO |  | 1
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 6: Order History | Task 6.2 Order History API | Get Order History | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 6: Order History | Task 6.2 Order History API | Order Detail | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 6: Order History | Task 6.3 History Testing |  | Task | TODO |  | 1
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 6: Order History | Task 6.3 History Testing | History Display Test | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 6: Order History | Task 6.3 History Testing | Detail Test | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 7: Product Review |  |  | Story | TODO |  | 3
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 7: Product Review | Task 7.1 Review UI |  | Task | TODO |  | 1
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 7: Product Review | Task 7.1 Review UI | Rating Component | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 7: Product Review | Task 7.1 Review UI | Comment Box | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 7: Product Review | Task 7.1 Review UI | Upload Review Image | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 7: Product Review | Task 7.2 Review API |  | Task | TODO |  | 1
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 7: Product Review | Task 7.2 Review API | Submit Review | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 7: Product Review | Task 7.2 Review API | Edit Review | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 7: Product Review | Task 7.2 Review API | Delete Review | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 7: Product Review | Task 7.3 Review Testing |  | Task | TODO |  | 1
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 7: Product Review | Task 7.3 Review Testing | Rating Test | Subtask | TODO
Sprint 2 | EPIC 3: Customer Shopping Experience | Story 7: Product Review | Task 7.3 Review Testing | Comment Test | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management |  |  |  | Epic | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch |  |  | Story | TODO |  | 8
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.1 Branch CRUD |  | Task | TODO |  | 3
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.1 Branch CRUD | Create Branch | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.1 Branch CRUD | Update Branch | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.1 Branch CRUD | Delete Branch | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.1 Branch CRUD | View Branch | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.2 Branch Information |  | Task | TODO |  | 3
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.2 Branch Information | Branch Address | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.2 Branch Information | Working Hours | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.2 Branch Information | Contact Information | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.2 Branch Information | Branch Images | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.3 Branch Testing |  | Task | TODO |  | 2
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.3 Branch Testing | CRUD Test | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 8: Manage Branch | Task 8.3 Branch Testing | Validation Test | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 9: Find Nearby Branch |  |  | Story | TODO |  | 5
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 9: Find Nearby Branch | Task 9.1 Location Service |  | Task | TODO |  | 2
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 9: Find Nearby Branch | Task 9.1 Location Service | Request User Location | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 9: Find Nearby Branch | Task 9.1 Location Service | Calculate Distance | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 9: Find Nearby Branch | Task 9.1 Location Service | Display Nearby Branches | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 9: Find Nearby Branch | Task 9.2 Nearby Branch API |  | Task | TODO |  | 2
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 9: Find Nearby Branch | Task 9.2 Nearby Branch API | Search Nearby Branch | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 9: Find Nearby Branch | Task 9.2 Nearby Branch API | Sort by Distance | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 9: Find Nearby Branch | Task 9.3 Testing |  | Task | TODO |  | 1
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 9: Find Nearby Branch | Task 9.3 Testing | GPS Test | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 9: Find Nearby Branch | Task 9.3 Testing | Distance Accuracy Test | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 10: Store Locator Map |  |  | Story | TODO |  | 5
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 10: Store Locator Map | Task 10.1 Google Maps Integration |  | Task | TODO |  | 2
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 10: Store Locator Map | Task 10.1 Google Maps Integration | Display Google Map | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 10: Store Locator Map | Task 10.1 Google Maps Integration | Add Branch Marker | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 10: Store Locator Map | Task 10.1 Google Maps Integration | Cluster Marker | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 10: Store Locator Map | Task 10.2 Branch Marker |  | Task | TODO |  | 2
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 10: Store Locator Map | Task 10.2 Branch Marker | Click Marker | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 10: Store Locator Map | Task 10.2 Branch Marker | Show Branch Information | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 10: Store Locator Map | Task 10.2 Branch Marker | Zoom to Branch | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 10: Store Locator Map | Task 10.3 Map Testing |  | Task | TODO |  | 1
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 10: Store Locator Map | Task 10.3 Map Testing | Marker Display Test | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 10: Store Locator Map | Task 10.3 Map Testing | Map Loading Test | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 11: Branch Detail |  |  | Story | TODO |  | 3
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 11: Branch Detail | Task 11.1 Branch Detail UI |  | Task | TODO |  | 1
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 11: Branch Detail | Task 11.1 Branch Detail UI | Display Images | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 11: Branch Detail | Task 11.1 Branch Detail UI | Display Working Hours | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 11: Branch Detail | Task 11.1 Branch Detail UI | Display Contact | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 11: Branch Detail | Task 11.2 Branch Detail API |  | Task | TODO |  | 1
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 11: Branch Detail | Task 11.2 Branch Detail API | Get Branch Detail | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 11: Branch Detail | Task 11.2 Branch Detail API | Get Branch Gallery | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 11: Branch Detail | Task 11.3 Testing |  | Task | TODO |  | 1
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 11: Branch Detail | Task 11.3 Testing | Detail Display Test | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 11: Branch Detail | Task 11.3 Testing | Image Loading Test | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 12: Navigation |  |  | Story | TODO |  | 3
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 12: Navigation | Task 12.1 Navigation Integration |  | Task | TODO |  | 1
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 12: Navigation | Task 12.1 Navigation Integration | Open Google Maps | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 12: Navigation | Task 12.1 Navigation Integration | Get Directions | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 12: Navigation | Task 12.2 Route Information |  | Task | TODO |  | 1
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 12: Navigation | Task 12.2 Route Information | Display Estimated Time | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 12: Navigation | Task 12.2 Route Information | Display Distance | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 12: Navigation | Task 12.3 Navigation Testing |  | Task | TODO |  | 1
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 12: Navigation | Task 12.3 Navigation Testing | Route Test | Subtask | TODO
Sprint 2 | EPIC 4: Branch & Store Locator Management | Story 12: Navigation | Task 12.3 Navigation Testing | Navigation Link Test | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management |  |  |  | Epic | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management |  |  | Story | TODO | Critical | 8 | Là nhân viên và quản trị viên, tôi muốn quản lý các đơn hàng trực tuyến để theo dõi, cập nhật trạng thái và xử lý đơn hàng hiệu quả.
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.1 Order Management UI |  | Task | TODO | Medium | 3
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.1 Order Management UI | Design Order List Page | Subtask | TODO | Medium
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.1 Order Management UI | Design Order Detail Page | Subtask | TODO | Medium
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.1 Order Management UI | Display Customer Information | Subtask | TODO | Medium
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.1 Order Management UI | Display Ordered Products | Subtask | TODO | Medium
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.1 Order Management UI | Responsive Order Management UI | Subtask | TODO | Medium
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.2 Order Management API |  | Task | TODO | High | 3
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.2 Order Management API | Get Order List | Subtask | TODO | High
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.2 Order Management API | Get Order Detail | Subtask | TODO | High
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.2 Order Management API | Update Order Status | Subtask | TODO | High
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.2 Order Management API | Cancel Order | Subtask | TODO | High
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.2 Order Management API | Search Orders | Subtask | TODO | Medium
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.3 Order Testing |  | Task | TODO |  | 2
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.3 Order Testing | Order Status Update Test | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.3 Order Testing | Cancel Order Test | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 1: Online Order Management | Task 1.3 Order Testing | Search Order Test | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales |  |  | Story | TODO |  | 8
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.1 POS Interface |  | Task | TODO |  | 3
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.1 POS Interface | Design POS Screen | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.1 POS Interface | Product Search | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.1 POS Interface | Add Product to Invoice | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.1 POS Interface | Update Quantity | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.1 POS Interface | Remove Product | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.2 POS API |  | Task | TODO |  | 3
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.2 POS API | Create Invoice | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.2 POS API | Calculate Total | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.2 POS API | Save Invoice | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.2 POS API | Update Inventory | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.2 POS API | Print Invoice Data | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.3 POS Testing |  | Task | TODO |  | 2
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.3 POS Testing | Create Invoice Test | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.3 POS Testing | Print Invoice Test | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 2: POS Sales | Task 2.3 POS Testing | Inventory Update Test | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 3: Sales Invoice |  |  | Story | TODO |  | 5
Sprint 3 | EPIC 5: Order & POS Management | Story 3: Sales Invoice | Task 3.1 Invoice UI |  | Task | TODO |  | 2
Sprint 3 | EPIC 5: Order & POS Management | Story 3: Sales Invoice | Task 3.1 Invoice UI | Invoice Detail | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 3: Sales Invoice | Task 3.1 Invoice UI | Customer Information | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 3: Sales Invoice | Task 3.1 Invoice UI | Payment Information | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 3: Sales Invoice | Task 3.2 Invoice API |  | Task | TODO |  | 2
Sprint 3 | EPIC 5: Order & POS Management | Story 3: Sales Invoice | Task 3.2 Invoice API | Generate Invoice | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 3: Sales Invoice | Task 3.2 Invoice API | Export Invoice PDF | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 3: Sales Invoice | Task 3.2 Invoice API | Send Invoice Email | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 3: Sales Invoice | Task 3.3 Invoice Testing |  | Task | TODO |  | 1
Sprint 3 | EPIC 5: Order & POS Management | Story 3: Sales Invoice | Task 3.3 Invoice Testing | Invoice Export Test | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 3: Sales Invoice | Task 3.3 Invoice Testing | Invoice Email Test | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 4: Birthday Cake Order |  |  | Story | TODO |  | 5
Sprint 3 | EPIC 5: Order & POS Management | Story 4: Birthday Cake Order | Task 4.1 Cake Order UI |  | Task | TODO |  | 2
Sprint 3 | EPIC 5: Order & POS Management | Story 4: Birthday Cake Order | Task 4.1 Cake Order UI | Cake Information Form | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 4: Birthday Cake Order | Task 4.1 Cake Order UI | Delivery Date Picker | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 4: Birthday Cake Order | Task 4.1 Cake Order UI | Cake Message Input | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 4: Birthday Cake Order | Task 4.2 Cake Order API |  | Task | TODO |  | 2
Sprint 3 | EPIC 5: Order & POS Management | Story 4: Birthday Cake Order | Task 4.2 Cake Order API | Save Cake Order | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 4: Birthday Cake Order | Task 4.2 Cake Order API | Update Cake Order | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 4: Birthday Cake Order | Task 4.2 Cake Order API | Cancel Cake Order | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 4: Birthday Cake Order | Task 4.3 Cake Order Testing |  | Task | TODO |  | 1
Sprint 3 | EPIC 5: Order & POS Management | Story 4: Birthday Cake Order | Task 4.3 Cake Order Testing | Create Cake Order Test | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 4: Birthday Cake Order | Task 4.3 Cake Order Testing | Delivery Date Validation | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management |  |  | Story | TODO |  | 5
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.1 Status Workflow |  | Task | TODO |  | 2
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.1 Status Workflow | Pending | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.1 Status Workflow | Confirmed | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.1 Status Workflow | Preparing | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.1 Status Workflow | Ready | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.1 Status Workflow | Completed | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.1 Status Workflow | Cancelled | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.2 Status Notification |  | Task | TODO |  | 2
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.2 Status Notification | Email Notification | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.2 Status Notification | In-app Notification | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.2 Status Notification | Status History | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.3 Status Testing |  | Task | TODO |  | 1
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.3 Status Testing | Status Change Test | Subtask | TODO
Sprint 3 | EPIC 5: Order & POS Management | Story 5: Order Status Management | Task 5.3 Status Testing | Notification Test | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management |  |  |  | Epic | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher |  |  | Story | TODO |  | 5
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.1 Voucher CRUD |  | Task | TODO |  | 2
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.1 Voucher CRUD | Create Voucher | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.1 Voucher CRUD | Update Voucher | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.1 Voucher CRUD | Delete Voucher | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.1 Voucher CRUD | Activate Voucher | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.2 Voucher Rules |  | Task | TODO |  | 2
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.2 Voucher Rules | Discount Type | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.2 Voucher Rules | Discount Value | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.2 Voucher Rules | Expiration Date | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.2 Voucher Rules | Minimum Order | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.3 Voucher Testing |  | Task | TODO |  | 1
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.3 Voucher Testing | Create Voucher Test | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 6: Manage Voucher | Task 6.3 Voucher Testing | Expired Voucher Test | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 7: Apply Voucher |  |  | Story | TODO |  | 5
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 7: Apply Voucher | Task 7.1 Voucher Validation |  | Task | TODO |  | 2
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 7: Apply Voucher | Task 7.1 Voucher Validation | Check Voucher Code | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 7: Apply Voucher | Task 7.1 Voucher Validation | Check Expiration | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 7: Apply Voucher | Task 7.1 Voucher Validation | Check Order Condition | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 7: Apply Voucher | Task 7.2 Apply Discount |  | Task | TODO |  | 2
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 7: Apply Voucher | Task 7.2 Apply Discount | Calculate Discount | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 7: Apply Voucher | Task 7.2 Apply Discount | Update Order Total | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 7: Apply Voucher | Task 7.2 Apply Discount | Display Discount | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 7: Apply Voucher | Task 7.3 Testing |  | Task | TODO |  | 1
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 7: Apply Voucher | Task 7.3 Testing | Valid Voucher Test | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 7: Apply Voucher | Task 7.3 Testing | Invalid Voucher Test | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 8: Banner Management |  |  | Story | TODO |  | 3
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 8: Banner Management | Task 8.1 Banner CRUD |  | Task | TODO |  | 1
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 8: Banner Management | Task 8.1 Banner CRUD | Upload Banner | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 8: Banner Management | Task 8.1 Banner CRUD | Update Banner | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 8: Banner Management | Task 8.1 Banner CRUD | Delete Banner | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 8: Banner Management | Task 8.2 Banner Display |  | Task | TODO |  | 1
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 8: Banner Management | Task 8.2 Banner Display | Homepage Banner | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 8: Banner Management | Task 8.2 Banner Display | Promotion Banner | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 8: Banner Management | Task 8.3 Banner Testing |  | Task | TODO |  | 1
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 8: Banner Management | Task 8.3 Banner Testing | Banner Upload Test | Subtask | TODO
Sprint 3 | EPIC 6: Promotion & Marketing Management | Story 8: Banner Management | Task 8.3 Banner Testing | Banner Display Test | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management |  |  |  | Epic | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory |  |  | Story | TODO | Critical | 8 | Là quản lý cửa hàng, tôi muốn quản lý tồn kho theo từng chi nhánh để kiểm soát số lượng sản phẩm và nguyên liệu.
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.1 Inventory Management UI |  | Task | TODO | Medium | 3
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.1 Inventory Management UI | Design Inventory List | Subtask | TODO | Medium
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.1 Inventory Management UI | Display Product Stock | Subtask | TODO | Medium
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.1 Inventory Management UI | Display Branch Stock | Subtask | TODO | Medium
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.1 Inventory Management UI | Search Inventory | Subtask | TODO | Medium
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.1 Inventory Management UI | Responsive Inventory Page | Subtask | TODO | Medium
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.2 Inventory API |  | Task | TODO |  | 3
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.2 Inventory API | Get Inventory List | Subtask | TODO | High
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.2 Inventory API | Get Branch Inventory | Subtask | TODO | High
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.2 Inventory API | Update Inventory | Subtask | TODO | High
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.2 Inventory API | Inventory History | Subtask | TODO | Medium
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.3 Inventory Testing |  | Task | TODO |  | 2
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.3 Inventory Testing | Inventory CRUD Test | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.3 Inventory Testing | Branch Inventory Test | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 1: Branch Inventory | Task 1.3 Inventory Testing | Stock Update Test | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 2: Update Stock |  |  | Story | TODO |  | 5
Sprint 4 | EPIC 7: Product & Inventory Management | Story 2: Update Stock | Task 2.1 Stock Update |  | Task | TODO |  | 2
Sprint 4 | EPIC 7: Product & Inventory Management | Story 2: Update Stock | Task 2.1 Stock Update | Increase Stock | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 2: Update Stock | Task 2.1 Stock Update | Decrease Stock | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 2: Update Stock | Task 2.1 Stock Update | Manual Stock Adjustment | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 2: Update Stock | Task 2.2 Stock Synchronization |  | Task | TODO |  | 2
Sprint 4 | EPIC 7: Product & Inventory Management | Story 2: Update Stock | Task 2.2 Stock Synchronization | Sync After Sale | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 2: Update Stock | Task 2.2 Stock Synchronization | Sync After Import | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 2: Update Stock | Task 2.2 Stock Synchronization | Sync After Cancellation | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 2: Update Stock | Task 2.3 Stock Testing |  | Task | TODO |  | 1
Sprint 4 | EPIC 7: Product & Inventory Management | Story 2: Update Stock | Task 2.3 Stock Testing | Increase Stock Test | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 2: Update Stock | Task 2.3 Stock Testing | Decrease Stock Test | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 3: Low Stock Warning |  |  | Story | TODO |  | 5
Sprint 4 | EPIC 7: Product & Inventory Management | Story 3: Low Stock Warning | Task 3.1 Low Stock Configuration |  | Task | TODO |  | 2
Sprint 4 | EPIC 7: Product & Inventory Management | Story 3: Low Stock Warning | Task 3.1 Low Stock Configuration | Configure Minimum Quantity | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 3: Low Stock Warning | Task 3.1 Low Stock Configuration | Configure Alert Threshold | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 3: Low Stock Warning | Task 3.1 Low Stock Configuration | Save Configuration | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 3: Low Stock Warning | Task 3.2 Alert Notification |  | Task | TODO |  | 2
Sprint 4 | EPIC 7: Product & Inventory Management | Story 3: Low Stock Warning | Task 3.2 Alert Notification | Dashboard Alert | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 3: Low Stock Warning | Task 3.2 Alert Notification | Email Alert | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 3: Low Stock Warning | Task 3.2 Alert Notification | Notification Badge | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 3: Low Stock Warning | Task 3.3 Testing |  | Task | TODO |  | 1
Sprint 4 | EPIC 7: Product & Inventory Management | Story 3: Low Stock Warning | Task 3.3 Testing | Alert Trigger Test | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 3: Low Stock Warning | Task 3.3 Testing | Threshold Validation | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 4: Expiry Warning |  |  | Story | TODO |  | 5
Sprint 4 | EPIC 7: Product & Inventory Management | Story 4: Expiry Warning | Task 4.1 Expiry Management |  | Task | TODO |  | 2
Sprint 4 | EPIC 7: Product & Inventory Management | Story 4: Expiry Warning | Task 4.1 Expiry Management | Add Expiry Date | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 4: Expiry Warning | Task 4.1 Expiry Management | Update Expiry Date | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 4: Expiry Warning | Task 4.1 Expiry Management | Track Expiry | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 4: Expiry Warning | Task 4.2 Expiry Notification |  | Task | TODO |  | 2
Sprint 4 | EPIC 7: Product & Inventory Management | Story 4: Expiry Warning | Task 4.2 Expiry Notification | Expiry Dashboard | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 4: Expiry Warning | Task 4.2 Expiry Notification | Expiry Email | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 4: Expiry Warning | Task 4.2 Expiry Notification | Product Expiry Report | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 4: Expiry Warning | Task 4.3 Testing |  | Task | TODO |  | 1
Sprint 4 | EPIC 7: Product & Inventory Management | Story 4: Expiry Warning | Task 4.3 Testing | Expiry Warning Test | Subtask | TODO
Sprint 4 | EPIC 7: Product & Inventory Management | Story 4: Expiry Warning | Task 4.3 Testing | Notification Test | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics |  |  |  | Epic | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview |  |  | Story | TODO |  | 5
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview | Task 5.1 Dashboard UI |  | Task | TODO |  | 2
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview | Task 5.1 Dashboard UI | Dashboard Layout | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview | Task 5.1 Dashboard UI | Revenue Cards | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview | Task 5.1 Dashboard UI | Order Cards | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview | Task 5.1 Dashboard UI | Customer Cards | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview | Task 5.2 Dashboard API |  | Task | TODO |  | 2
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview | Task 5.2 Dashboard API | Revenue Summary | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview | Task 5.2 Dashboard API | Daily Orders | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview | Task 5.2 Dashboard API | Customer Summary | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview | Task 5.3 Testing |  | Task | TODO |  | 1
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview | Task 5.3 Testing | Dashboard Display Test | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 5: Dashboard Overview | Task 5.3 Testing | API Response Test | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report |  |  | Story | TODO |  | 8
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.1 Revenue Statistics |  | Task | TODO |  | 3
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.1 Revenue Statistics | Daily Revenue | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.1 Revenue Statistics | Weekly Revenue | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.1 Revenue Statistics | Monthly Revenue | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.1 Revenue Statistics | Yearly Revenue | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.2 Revenue Charts |  | Task | TODO |  | 3
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.2 Revenue Charts | Bar Chart | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.2 Revenue Charts | Line Chart | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.2 Revenue Charts | Pie Chart | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.2 Revenue Charts | Export Excel | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.3 Testing |  | Task | TODO |  | 2
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.3 Testing | Revenue Calculation Test | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 6: Revenue Report | Task 6.3 Testing | Chart Display Test | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 7: Best Selling Products |  |  | Story | TODO |  | 5
Sprint 4 | EPIC 8: Reporting & Analytics | Story 7: Best Selling Products | Task 7.1 Best Seller Report |  | Task | TODO |  | 2
Sprint 4 | EPIC 8: Reporting & Analytics | Story 7: Best Selling Products | Task 7.1 Best Seller Report | Product Ranking | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 7: Best Selling Products | Task 7.1 Best Seller Report | Top 10 Products | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 7: Best Selling Products | Task 7.1 Best Seller Report | Category Ranking | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 7: Best Selling Products | Task 7.2 Report Export |  | Task | TODO |  | 2
Sprint 4 | EPIC 8: Reporting & Analytics | Story 7: Best Selling Products | Task 7.2 Report Export | Export Excel | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 7: Best Selling Products | Task 7.2 Report Export | Export PDF | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 7: Best Selling Products | Task 7.2 Report Export | Print Report | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 7: Best Selling Products | Task 7.3 Testing |  | Task | TODO |  | 1
Sprint 4 | EPIC 8: Reporting & Analytics | Story 7: Best Selling Products | Task 7.3 Testing | Ranking Test | Subtask | TODO
Sprint 4 | EPIC 8: Reporting & Analytics | Story 7: Best Selling Products | Task 7.3 Testing | Export Test | Subtask | TODO
Sprint 4 | EPIC 9: Review & Feedback Management |  |  |  | Epic | TODO
Sprint 4 | EPIC 9: Review & Feedback Management | Story 8: Review Moderation |  |  | Story | TODO |  | 3
Sprint 4 | EPIC 9: Review & Feedback Management | Story 8: Review Moderation | Task 8.1 Review Management |  | Task | TODO |  | 1
Sprint 4 | EPIC 9: Review & Feedback Management | Story 8: Review Moderation | Task 8.1 Review Management | View Reviews | Subtask | TODO
Sprint 4 | EPIC 9: Review & Feedback Management | Story 8: Review Moderation | Task 8.1 Review Management | Search Reviews | Subtask | TODO
Sprint 4 | EPIC 9: Review & Feedback Management | Story 8: Review Moderation | Task 8.1 Review Management | Filter Reviews | Subtask | TODO
Sprint 4 | EPIC 9: Review & Feedback Management | Story 8: Review Moderation | Task 8.2 Review Moderation |  | Task | TODO |  | 1
Sprint 4 | EPIC 9: Review & Feedback Management | Story 8: Review Moderation | Task 8.2 Review Moderation | Hide Review | Subtask | TODO
Sprint 4 | EPIC 9: Review & Feedback Management | Story 8: Review Moderation | Task 8.2 Review Moderation | Delete Review | Subtask | TODO
Sprint 4 | EPIC 9: Review & Feedback Management | Story 8: Review Moderation | Task 8.2 Review Moderation | Restore Review | Subtask | TODO
Sprint 4 | EPIC 9: Review & Feedback Management | Story 8: Review Moderation | Task 8.3 Testing |  | Task | TODO |  | 1
Sprint 4 | EPIC 9: Review & Feedback Management | Story 8: Review Moderation | Task 8.3 Testing | Hide Review Test | Subtask | TODO
Sprint 4 | EPIC 9: Review & Feedback Management | Story 8: Review Moderation | Task 8.3 Testing | Delete Review Test | Subtask | TODO
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance |  |  |  | Epic | TODO
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing |  |  | Story | TODO | High | 8 | Là nhóm phát triển, chúng tôi muốn kiểm thử từng module để đảm bảo mọi chức năng hoạt động đúng trước khi tích hợp.
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.1 Backend Unit Testing |  | Task | TODO |  | 3
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.1 Backend Unit Testing | Test Authentication Module | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.1 Backend Unit Testing | Test Product Module | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.1 Backend Unit Testing | Test Order Module | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.1 Backend Unit Testing | Test Inventory Module | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.1 Backend Unit Testing | Test Report Module | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.2 Frontend Unit Testing |  | Task | TODO |  | 3
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.2 Frontend Unit Testing | Test Login Component | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.2 Frontend Unit Testing | Test Product Component | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.2 Frontend Unit Testing | Test Cart Component | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.2 Frontend Unit Testing | Test Checkout Component | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.2 Frontend Unit Testing | Test Dashboard Component | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.3 Unit Test Report |  | Task | TODO |  | 2
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.3 Unit Test Report | Generate Unit Test Report | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.3 Unit Test Report | Review Failed Test Cases | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 1: Unit Testing | Task 1.3 Unit Test Report | Fix Unit Test Errors | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing |  |  | Story | TODO | High | 8
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.1 API Integration Testing |  | Task | TODO |  | 3
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.1 API Integration Testing | Authentication API | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.1 API Integration Testing | Product API | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.1 API Integration Testing | Order API | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.1 API Integration Testing | Inventory API | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.1 API Integration Testing | Report API | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.2 Frontend Integration |  | Task | TODO |  | 3
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.2 Frontend Integration | Login Flow | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.2 Frontend Integration | Shopping Flow | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.2 Frontend Integration | Checkout Flow | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.2 Frontend Integration | Admin Dashboard Flow | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.3 Integration Report |  | Task | TODO |  | 2
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.3 Integration Report | Generate Test Report | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.3 Integration Report | Review Integration Errors | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 2: Integration Testing | Task 2.3 Integration Report | Fix Integration Issues | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 3: Security Testing |  |  | Story | TODO | High | 5
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 3: Security Testing | Task 3.1 Authentication Security |  | Task | TODO |  | 2
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 3: Security Testing | Task 3.1 Authentication Security | SQL Injection Test | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 3: Security Testing | Task 3.1 Authentication Security | XSS Test | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 3: Security Testing | Task 3.1 Authentication Security | JWT Validation | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 3: Security Testing | Task 3.2 API Security |  | Task | TODO |  | 2
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 3: Security Testing | Task 3.2 API Security | Authorization Test | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 3: Security Testing | Task 3.2 API Security | Permission Validation | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 3: Security Testing | Task 3.2 API Security | API Rate Limit Test | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 3: Security Testing | Task 3.3 Security Report |  | Task | TODO |  | 1
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 3: Security Testing | Task 3.3 Security Report | Security Report | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 3: Security Testing | Task 3.3 Security Report | Fix Vulnerabilities | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 4: Performance Optimization |  |  | Story | TODO | Medium | 5
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 4: Performance Optimization | Task 4.1 Backend Optimization |  | Task | TODO |  | 2
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 4: Performance Optimization | Task 4.1 Backend Optimization | Optimize Database Queries | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 4: Performance Optimization | Task 4.1 Backend Optimization | Add Database Indexes | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 4: Performance Optimization | Task 4.1 Backend Optimization | Optimize API Response | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 4: Performance Optimization | Task 4.2 Frontend Optimization |  | Task | TODO |  | 2
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 4: Performance Optimization | Task 4.2 Frontend Optimization | Lazy Loading | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 4: Performance Optimization | Task 4.2 Frontend Optimization | Image Optimization | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 4: Performance Optimization | Task 4.2 Frontend Optimization | Bundle Optimization | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 4: Performance Optimization | Task 4.3 Performance Testing |  | Task | TODO |  | 1
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 4: Performance Optimization | Task 4.3 Performance Testing | Load Testing | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 4: Performance Optimization | Task 4.3 Performance Testing | Stress Testing | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment |  |  | Story | TODO | High | 8
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.1 Backend Deployment |  | Task | TODO |  | 3
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.1 Backend Deployment | Configure Production Environment | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.1 Backend Deployment | Deploy Backend | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.1 Backend Deployment | Configure Environment Variables | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.1 Backend Deployment | Verify API Health Check | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.2 Frontend Deployment |  | Task | TODO |  | 3
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.2 Frontend Deployment | Build Production Version | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.2 Frontend Deployment | Deploy Frontend | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.2 Frontend Deployment | Configure Domain | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.2 Frontend Deployment | Configure HTTPS | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.3 Deployment Validation |  | Task | TODO |  | 2
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.3 Deployment Validation | Smoke Testing | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.3 Deployment Validation | Verify Database Connection | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.3 Deployment Validation | Verify Production APIs | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 5: Production Deployment | Task 5.3 Deployment Validation | Verify Login Functionality | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance |  |  | Story | TODO | High | 5
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.1 Bug Fixing |  | Task | TODO |  | 2
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.1 Bug Fixing | Fix Authentication Bugs | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.1 Bug Fixing | Fix Product Bugs | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.1 Bug Fixing | Fix Order Bugs | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.1 Bug Fixing | Fix Inventory Bugs | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.2 Documentation |  | Task | TODO |  | 2
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.2 Documentation | Update API Documentation | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.2 Documentation | Update User Guide | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.2 Documentation | Update Deployment Guide | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.3 Final Review |  | Task | TODO |  | 1
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.3 Final Review | Sprint Review | Subtask | TODO | High
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.3 Final Review | Retrospective Meeting | Subtask | TODO | Medium
Sprint 5 | EPIC 10: Testing, Deployment & Maintenance | Story 6: Bug Fixing & Maintenance | Task 6.3 Final Review | Final Project Handover | Subtask | TODO | High

## Dashboard
Sprint Breakdown
Sprint | Total SP
Sprint 1 | 35
Sprint 2 | 64
Sprint 3 | 44
Sprint 4 | 44
Sprint 5 | 39
Epic Breakdown
Epic | Total SP
EPIC 10: Testing, Deployment & Maintenance | 39
EPIC 2: Product & Inventory Management | 35
EPIC 3: Customer Shopping Experience | 40
EPIC 4: Branch & Store Locator Management | 24
EPIC 5: Order & POS Management | 31
EPIC 6: Promotion & Marketing Management | 13
EPIC 7: Product & Inventory Management | 23
EPIC 8: Reporting & Analytics | 18
EPIC 9: Review & Feedback Management | 3